## Sheet1
|  |  |  | Scope | [10 empty] | 10 footings
|  |  |  | Time - d | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 10 day
|  |  |  | Cost -usd | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 1000 usd
CDD
| Budget at Completion | BAC | 1000
After 5 Days
BCWS | Planned Value | PV | 5*100 | 500
After 5 days; 3 footings
BCWP | Earned Value | EV | 3*100 | 300
150usd/Footing
ACWP | Actual Cost | AC | 3*150 | 450
Variance Analysis
| Schedule Variance | SV | EV-PV | -200 | If (-) Behind the Schedule; If (+) Ahead of the Schedule
| Cost Variance | CV | EV-AC | -150 | If (-) Over Budget; If (+) Under Budget
Performance Index
| Schedule Performance Index | SPI | EV/PV | 0.6 | If SPI<1; Behind the Schedule
| Cost Performance Index | CPI | EV/AC | 0.66667 | If CPI<1; Over Budget
| Estimate at Completion | EAC | BAC/CPI | 1500
| Estimate to Complete | ETC | EAC-AC | 1050
| Variance at Completion | VAC | BAC-EAC | -500